## Sheet1
Paul Wallace
Easy Notes Project Plan
Updated on 11/14/2012
PaulWallacc@gmail.com
| MileStone | Start Date | End Date | Week 1 8/27-9/1 | Week 2 9/2-9/8 | Week 3 ¦¦ 9/9-9/15 | Week 4 ¦¦ 6/16-9/22 | Week 5 ¦¦ 9/23-9/29 | Week 6 ¦¦ 9/30-10/6 | Week 7 ¦¦ 10/7-10/13 | Week 8 ¦¦ 10/14-10/20 | Week 9 ¦¦ 10/21-10/27 | Week 10 ¦¦ 10/28-11/3 | Week 11 ¦¦ 11/4-11/10 | Week 12 ¦¦ 11/11-11/17 | Week 13 ¦¦ 11/18-11/24 | Week 14 ¦¦ 11/25-12/1 | Week 15 ¦¦ 12/2-12/8 | Week 16 ¦¦ 12/9-12/15 | Week 17 ¦¦ 12/16-12/22
Thanksgiving Break
1 | Project Proposal | Week 1 | Week 2
2 | SRS Doc | Week 2 | Week 3
3 | User Stories | Week 3 | Week 4
4 | Project Pan | Week 4 | Week 5
5
6 | Layout screens on paper
7 | Layout the home and notes list screens. Identify where the buttons will be placed.
8 | Create Toasts for all of the buttons to test the listeners
9 | Get a simple ViewPagerAdapter functioning - test swipe funcionality
10 | Create a simple NoteRow class to define each note
11 | Write logic to pull information from the inputs on button press
12 | Create the notes list adapter to populate the list with notes
13 | Write logic to take the user input and pass it to the adapter to populate the list view
14 | Set up the SQLLite database to remember notes upon application shutdown
15 | Write logic to show date and time pickers
16 | Add an onItemClickListener to be able to select notes.
17 | Set up Toasts to test 16.
18 | Create dialog that appears onItemSelected
19 | Create Layout for dialog - same as first pane
20 | Add the button listeners and date time pickers.
21 | Write logic that updates the SQLLite database if the data is changed
22 | Add code to hide keyboard on button press
23 | Add an OnItemLongClickListener for note deletion
24 | Create a simple dialog to delete note on long item click
25 | Add logic to the Database helper to delete notes by id.
26 | Test all of the functionality
27 | Add images to the buttons
28 | Add a splash screen that is viewed on startup
29 | Test Functionality
30 | Publish application version 1 to the android marketplace
31
32 | Out of scope To do:
33 | Add NFC Functionality
34 | Add a help button that displays a dialog with help text.
35 | Fix any errors that may arise.
36 | Alarm Clock
37 | Delete date
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57